## Sheet1
project_description | project_type | project_subtype | contact | lab | date_request | duration_hrs | completed | remarks
Single Cell Analysis of Mouse Pancreatic Cancer | Single Cell | DE + GSEA | Melanie Guyot | Bergers/Lambrechts | 2020-08-18 | 200 | Unfinished | joint project between Bergers and Lambrechts lab
Monocle 3 Single Cell Trajectory Analysis | Single Cell | Trajectory Analysis | Nuphar Veiga | Carmeliet | 2020-08-20 | 20 | N | project was requested for a publication and then stated that it was no longer needed
Assistance in TPM to FPM count conversion | Single Cell | Data processing | Gonca Durdag | Lambrechts | 2020-08-21 | 1 | Y | requested help in developing script to convert between count types
TCGA/CCLE meQTL Benchmark Data | Epigenetics | Benchmarking | Francesca Lodi | Lambrechts | 2020-08-25 | 1 | Y | project consisted of helping find the correct dataset to answer research question
Installation of MAGeCK-VISPR | CRISPR screen | Infrastucture | Ria Pinioti | Mazzone | 2020-08-31 | 3 | Y | help with installing Python, conda and Docker environments
Multivariate Analysis | Biostatistics | Biostatistics | Pierre von Mol | Lambrechts | 2020-09-02 | 5 | Y | statistical tests on covariates of COVID data
Bulk RNAseq Analysis of Mice Tumors | Bulk RNAseq | DE + GSEA | Patricia Manzano | Fendt | 2020-09-06 | 15 | Y | There were 2 versions of this analysis (i.e. different models)
Bulk RNAseq Analysis of Mice Tumors | Bulk RNAseq | DE + GSEA | Lindsay Broadfield | Fendt | 2020-09-06 | 40 | Y | There were 4 versions of this analysis (i.e. different models)
Implementing Bulk RNAseq Pipeline on VSC | Bulk RNAseq | Infrastucture | CCB | CCB | 2020-09-06 | 40 | Y | A bulk RNAseq pipeline was constructed because none currently existed
PDAC Data Storage and Retrieval | Single Cell | Data processing | Max Mazzone | Mazzone | 2020-09-16 | 8 | Y | Locating, transferring and storing files for PDAC project. This includes meetings and expertise
SNP Calling Pipeline for Single Cell Data | Single Cell | Infrastucture | Joanna Pozniak | Marine | 2020-09-07 | 40 | Y | A SNP calling pipeline was constructed to meet this request
Benchmarking expression of Ptgdr Genes in TCGA Melanoma | Single Cell | Benchmarking | Rosa Trotta | Mazzone | 2020-09-28 | 10 | Y | Seurat feature plots were generated for annotated cell types
Locating TCGA/CCLE Benchmark Data | Biostatistics | Biostatistics | Patricia Manzano | Fendt | 2020-09-29 | 3 | N | The desired data could not found
Analysis of CNV data | CNV | Infrastucture | Aurélie Bousard | Marine | 2020-09-29 | 2 | Y | requested advice for implementing CNV pipeline
GO and KEGG CRISPR-Cas target annotation | CRISPR screen | Infrastucture | Alejandro Cuadros | Fendt | 2020-10-14 | 5 | Y | A script was written to automatically annotate any list of CRISPR-Cas targets
Benchmarking and SCENIC analysis of TAM data | Single Cell | Benchmarking | Tommaso Scolaro | Mazzone | 2020-11-04 | 40 | Unfinished | This project consists of several parts, including benchmarking TCGA data, a correlation analysis to find co-expressing genes in macrophages, an scRNAseq analysis and a SCENIC analysis
Proteomic Analysis of Mice Tumors | Proteomic | DE + GSEA | Lindsay Broadfield | Fendt | 2020-11-20 | 40 | Y | Heatmaps for protemic, metabolomic and RNAseq data gene sets generated
FACS pipeline+ Shiny App | FACS | Infrastucture | Sanket More | Agostini | 2020-12-21 | 18 | Unfinished | This project will resume in March when Sanket is back from his honeymoon in India
Submit data to GEO for publication | Bulk RNAseq | Data processing | Lindsay Broadfield | Fendt | 2021-01-17 | 6 | Y | Help with gathering and submitting data for paper resubmission to GEO database
Bulk RNAseq Analysis of Mice Tumors | Bulk RNAseq | DE + GSEA | Patricia Manzano | Fendt | 2021-01-21 | 10 | Y | Extension of previous RNAseq analysis, this time with new samples
MAGeCK-VISPR CRISPR-Cas Analysis | CRISPR screen | Benchmarking | Mario di Matteo | Mazzone | 2021-01-21 | 25 | Unfinished | This analysis will generate genes for the benchmarking for Ria
Benchmarking expression of genes in TCGA in Tregs for Melanoma | Single Cell | Benchmarking | Ria Pinioti | Mazzone | 2021-01-21 | 25 | Unfinished | See above
Benchmarking expression of genes in TCGA Melanoma | Single Cell | Benchmarking | Silvia Rivis | Mazzone | 2021-01-26 | 22 | Unfinished | Benchmarking in 4 different datasets
Benchmarking expression of autophagy genes in TCGA Melanoma | Single Cell | Benchmarking | Jelle Verhoeven | Agostini | 2021-02-02 | 5 | Unfinished | Benchmarking in 1 dataset
WES Copy Number Pipeline | WES CN | Infrastucture | Joanna Pozniak | Marine | 2021-02-10 | 1 | Unfinished | This question was transferred to Bram, who has ran WES copy number analyses before, however I many end up taking up this project in Joanna needs help
Upstream Regulator Analysis and GSEA | Epigenetics | Regulatory Analysis | Carla Domingo | Mazzone | 2021-02-11 | 4 | Unfinished | Calra requested help in interpreting gene regulatory information with respect to her gene of interest, TRAIL
Script to parse HDF5 Files for Single Cell Benchmarking | Single Cell | Infrastucture | Qun Zeng | Carmeliet | 2021-03-10 | 2 | Y | Qun is benchmarking Single Cell Data and needed help with a script to extract the necessary files
Benchmarking of SLC genes in Single Cell PDAC data | Single Cell | Benchmarking | Federica Cappellesso | Mazzone | 2021-03-15 | 5 | Y | Benchmarking in 1 dataset
Benchmarking of EIF2AK3/PERK in Single Cell data | Single Cell | Benchmarking | Sanket More | Agostini | 2021-03-17 | 8 | Unfinished | Benchmarking PERK in T-cells in two different datasets
Benchmarking Publically Available Methylation Datasets | Epigenetics | Benchmarking | Ewout Landeloos | Marine | 2021-03-22 | 1 | Unfinished | Ewout wants to test different methylation datasets and compare the results with his data